# 8- FISHERIES

## I- PRIORITY LIST

PRIORITY 8.1 Establishment of Legal Framework for the Alignment with the Common Fisheries Policy

Task 8.1 Structural Policies

Task 8.2 Conservation and Control Policy

Task 8.3 Marketing Policy

Task 8.4 Fisheries Vessel Registration System

Task 8.5 Information Systems and Statistics

Task 8.6 Food Hygiene in Fisheries

Task 8.7 Aquaculture

## II- MEASURES FOR HARMONISATION WITH THE EU LEGISLATION AND IMPLEMENTATION

### PRIORITY 8.1 Establishment of the Legal Framework for Alignment with the Common Fisheries Policy

##### 1-Priority Description

The lack of the administrative structure and legislation essential for the functioning of basic management mechanisms, in particular for the Financial Instrument for Fisheries Guidance (FIFG) and the Multi Annual Guidance Programme (MAGP), appear to be the main problems in the context of Turkey’s alignment process with the EU Common Fisheries Policy.

In this context, parallel to the 2003 Accession Partnership Document, alignment of Turkish legislation on fisheries management, control, marketing and structural adjustment with  the Community acquis is identified as a short-term priority. For the medium term, the objective is the re-organisation and strengthening of the institutional capacity of the fisheries administration; alignment of fisheries management, control and marketing and structural alignment in accordance with the EU acquis; development and implementation of a computerised fisheries vessel registration and statistical information system in compliance with the acquis.

In order to achieve these objectives, a project with the title of ‘Fisheries Sector-Legal and Institutional Alignment with the EU Acquis Project’ is proposed within the framework of the 2003 Pre-accession Financial Assistance Programme. The project will be successful only through the establishment of a Directorate General for Fisheries within the Ministry of Agriculture and Rural Affairs, or a similar autonomous body, and through the harmonisation of the legislation within the scope of the project in accordance with a timetable.

##### 2- Schedule of Necessary Legislative Changes

Table 8.1.1

| No | Title and Number of EU legislation | Title of Draft Turkish legislation | Responsible Institution | Proposed Date of the Approval of the Minister / Council of Ministers | Proposed Date of 1- Adoption by the Parliament 2- Entry into Force |
| --- | --- | --- | --- | --- | --- |
| Task 8.1 Structural Policies |
| 1 | 2792/1999/EC: Council Regulation (EC) No 2792/1999 of 17 December 1999 laying down the detailed rules and arrangements regarding Community structural assistance in the fisheries sector 1260/1999/EC: Council Regulation (EC) No 1260/1999 of 21 June 1999 laying down general provisions on the Structural Funds | Framework Law on Fisheries | Ministry of Agriculture and Rural Affairs (This legislation will be drafted with the participation of relevant institutions). | 30.06.2004 | 1- 15.06.2005 2- 15.07.2005 |
|  |  | Decision of Council of Ministers on the establishment of a mechanism providing monetary compensation in case vessels are excluded from fishing | Ministry of Agriculture and Rural Affairs (This legislation will be drafted with the participation of relevant institutions). | 30.06.2004 | 2-15.07.2005 |
|  |  | Implementing Regulation Amending the Implementing Regulation on Fisheries | Ministry of Agriculture and Rural Affairs (This legislation will be drafted with the participation of relevant institutions). | 30.06.2004 | 2-15.07.2005 |
| 2 | 366/2001/EC: Commission Regulation (EC) No 366/2001 of 22 February 2001 laying down detailed rules for implementing the measures provided for in Council Regulation (EC) No 2792/1999 | Framework Law on Fisheries | Ministry of Agriculture and Rural Affairs (This legislation will be drafted with the participation of relevant institutions). | 30.06.2004 | 1- 15.06.2005 2- 15.07.2005 |
|  |  | Implementing Regulation Amending the Implementing Regulation on Fisheries | Ministry of Agriculture and Rural Affairs (This legislation will be drafted with the participation of relevant institutions). | 30.06.2004 | 2- 15.07.2005 |

Table 8.1.1 (Continued)

| No | Title and Number of EU legislation | Title of Draft Turkish legislation | Responsible Institution | Proposed Date of the Approval of the Minister / Council of Ministers | Proposed Date of 1- Adoption by the Parliament 2- Entry into Force |
| --- | --- | --- | --- | --- | --- |
| 3 | 1263/1999/EC: Council Regulation (EC) No 1263/1999 of 21 June 1999 on the Financial Instrument for Fisheries Guidance | Framework Law on Fisheries | Ministry of Agriculture and Rural Affairs (This legislation will be drafted with the participation of relevant institutions). | 30.06.2004 | 1- 15.06.2005 2- 15.07.2005 |
|  |  | Decision of Council of Ministers on the establishment of a mechanism giving priority to the regional allocation of financial support in the fisheries sector | Ministry of Agriculture and Rural Affairs (This legislation will be drafted with the participation of relevant institutions). | 30.06.2004 | 2- 15.07.2005 |
| Task 8.2 Conservation and Control Policies |
| 1 | 3760/92/EEC: Council Regulation (EEC) No 3760/92 of 20 December 1992 establishing a Community system for fisheries and aquaculture 1626/94/EC: Council Regulation (EC) No 1626/94 of 27 June 1994 laying down certain technical measures for the conservation of fishery resources in the Mediterranean 2027/95/EC: Council Regulation (EC) No 2027/95 of 15 June 1995 establishing a system for the management of fishing effort relating to certain Community fishing areas and resources | Framework Law on Fisheries | Ministry of Agriculture and Rural Affairs (This legislation will be drafted with the participation of relevant institutions.) | 30.06.2004 | 1- 15.06.2005 2- 15.07.2005 |
|  |  | Implementing Regulation Amending the Implementing Regulation on Fisheries | Ministry of Agriculture and Rural Affairs (This legislation will be drafted with the participation of relevant institutions). | 30.06.2004 | 2- 15.07.2005 |

Table 8.1.1 (Continued)

| No | Title and Number of EU legislation | Title of Draft Turkish legislation | Responsible Institution | Proposed Date of the Approval of the Minister / Council of Ministers | Proposed Date of 1- Adoption by the Parliament 2- Entry into Force |
| --- | --- | --- | --- | --- | --- |
| 2 | 2847/93/EEC: Council Regulation (EEC) No 2847/93 of 12 October 1993 establishing a control system applicable to the common fisheries policy | Framework Law on Fisheries | Ministry of Agriculture and Rural Affairs (This legislation will be drafted with the participation of relevant institutions). | 30.06.2004 | 1- 15.06.2005 2- 15.07.2005 |
|  |  | Implementing Regulation Amending the Implementing Regulation on Fisheries | Ministry of Agriculture and Rural Affairs (This legislation will be drafted with the participation of relevant institutions). | 30.06.2004 | 2- 15.07.2005 |
|  |  | Circular on the improvement of the efficiency of penalties | Ministry of Agriculture and Rural Affairs (This legislation will be drafted with the participation of relevant institutions). | 30.06.2004 | 2- 15.07.2005 |
| 3 | 897/94/EC: Commission Regulation (EC) No 897/94 of 22 April 1994 laying down detailed rules for the application of Council Regulation (EEC) No 2847/93 as regards pilot projects relating to continuous position monitoring of Community fishing vessels | Circular on the implementation principles of vessel monitoring system | Ministry of Agriculture and Rural Affairs | 30.06.2004 | 2- 15.07.2005 |
|  | 1489/97/EC: Commission Regulation (EC) No 1489/97 of 29 July 1997 laying down detailed rules for the application of Council Regulation (EEC) No 2847/93 as regards satellite-based vessel monitoring systems |  |  |  |  |
| 4 | 1936/2001/EC: Council Regulation (EC) No 1936/2001 of 27 September 2001 laying down control measures applicable to fishing for certain stocks of highly migratory fish | Implementing Regulation Amending the Implementing Regulation on Fisheries | Ministry of Agriculture and Rural Affairs (This legislation will be drafted with the participation of relevant institutions). | 30.06.2004 | 2- 15.07.2005 |

Table 8.1.1 (Continued)

| No | Title and Number of EU legislation | Title of Draft Turkish legislation | Responsible Institution | Proposed Date of the Approval of the Minister / Council of Ministers | Proposed Date of 1- Adoption by the Parliament 2- Entry into Force |
| --- | --- | --- | --- | --- | --- |
| Task 8.3 Marketing Policy |
| 1 | 104/2000/EC: Council Regulation (EC) No 104/2000 of 17 December 1999 on the common organisation of the markets in fishery and aquaculture products | Framework Law on Fisheries | Ministry of Agriculture and Rural Affairs (This legislation will be drafted with the participation of relevant institutions). | 30.06.2004 | 1- 15.06.2005 2- 15.07.2005 |
|  |  | Law on Agricultural Producer Unions | Ministry of Agriculture and Rural Affairs | 2003, III. Quarter | 1- 2003, VI. Quarter 2- January 2004 |
|  |  | Implementing Regulation Amending the Implementing Regulation on Fisheries | Ministry of Agriculture and Rural Affairs (This legislation will be drafted with the participation of relevant institutions). | 30.06.2004 | 2- 15.07.2005 |
|  |  | Circular on Fisheries | Ministry of Agriculture and Rural Affairs (This legislation will be drafted with the participation of relevant institutions). | 30.06.2004 | 2- 15.07.2005 |
|  |  | Implementing Regulation Amending the Implementing Regulation on Wholesale and Retail Sale Places of Fishery Products | Ministry of Agriculture and Rural Affairs (This legislation will be drafted with the participation of relevant institutions). | 30.06.2004 | 2- 15.07.2005 |
| 2 | 79/112/EEC: Council Directive 79/112/EEC of 18 December 1978 on the approximation of the laws of the Member States relating to the labelling, presentation and advertising of foodstuffs for sale to the ultimate consumer | Circular on the labelling and presentation of fishery products supplied to the ultimate consumer | Ministry of Agriculture and Rural Affairs | 30.06.2004 | 2- 15.07.2005 |

Table 8.1.1 (Continued)

| No | Title and Number of EU legislation | Title of Draft Turkish legislation | Responsible Institution | Proposed Date of the Approval of the Minister / Council of Ministers | Proposed Date of 1- Adoption by the Parliament 2- Entry into Force |
| --- | --- | --- | --- | --- | --- |
| 3 | 2136/89/EEC: Council Regulation (EEC) No 2136/89 of 21 June 1989 laying down common marketing standards for preserved sardines | Circular on the implementation of common marketing standards for fisheries | Ministry of Agriculture and Rural Affairs | 30.06.2004 | 2- 15.07.2005 |
|  | 1536/92/EEC: Council Regulation (EEC) No 1536/92 of 9 June 1992 laying down common marketing standards for preserved tuna and bonito |  |  |  |  |
|  | 323/97/EC: Commission Regulation (EC) No 323/97 of 21 February 1997 amending Council Regulation (EC) No 2406/96 laying down common marketing standards for certain fishery products |  |  |  |  |
|  | 2578/2000/EC: Council Regulation (EC) No 2578/2000 of 17 November 2000 amending Regulation (EC) No 2406/96 laying down common marketing standards for certain fishery products |  |  |  |  |
|  | 2495/2001/EC: Commission Regulation (EC) No 2495/2001 of 19 December 2001 amending Council Regulation (EC) No 2406/96 laying down common marketing standards for certain fishery products |  |  |  |  |

Table 8.1.1 (Continued)

| No | Title and Number of EU legislation | Title of Draft Turkish legislation | Responsible Institution | Proposed Date of the Approval of the Minister / Council of Ministers | Proposed Date of 1- Adoption by the Parliament 2- Entry into Force |
| --- | --- | --- | --- | --- | --- |
| 4 | 2211/94 /EC: Commission Regulation (EC) No 2211/94 of 12 September 1994 laying down detailed rules for the implementation of Council Regulation (EEC) No 3759/92 as regards the notification of the prices of imported fishery products | Circular regulating the price notifications on imported fishery products | Ministry of Agriculture and Rural Affairs | 30.06.2004 | 2- 15.07.2005 |
| 5 | 1812/2001/EC: Commission Regulation (EC) No 1812/2001 of 14 September 2001 amending Regulation (EC) No 1886/2000 as regards the extension to non-members of certain rules adopted by producers' organisations in the fisheries sector | Circular on the implementation principles of producer organisations and price mechanisms in the fisheries market | Ministry of Agriculture and Rural Affairs | 30.06.2004 | 2- 15.07.2005 |
|  | 1886/2000/EC: Commission Regulation (EC) No 1886/2000 of 6 September 2000 laying down detailed rules for the application of Council Regulation (EC) No 104/2000 as regards the extension to non-members of certain rules adopted by producers' organisations in the fisheries sector |  |  |  |  |
|  | 1924/2000/EC: Commission Regulation (EC) No 1924/2000 of 11 September 2000 laying down detailed rules for the application of Council Regulation (EC) No 104/2000 as regards the grant of specific recognition to producers' organisations in the fisheries sector in order to improve the quality of their products |  |  |  |  |

Table 8.1.1 (Continued)

| No | Title and Number of EU legislation | Title of Draft Turkish legislation | Responsible Institution | Proposed Date of the Approval of the Minister / Council of Ministers | Proposed Date of 1- Adoption by the Parliament 2- Entry into Force |
| --- | --- | --- | --- | --- | --- |
|  | 2508/2000/EC: Commission Regulation (EC) No 2508/2000 of 15 November 2000 laying down the detailed rules for the application of Council Regulation (EC) No 104/2000 as regards operational programmes in the fisheries sector |  |  |  |  |
|  | 2509/2000/EC: Commission Regulation (EC) No 2509/2000 of 15 November 2000 laying down detailed rules for the application of Council Regulation (EC) No 104/2000 as regards granting financial compensation for withdrawals of certain fishery products |  |  |  |  |
|  | 2813/2000/EC: Commission Regulation (EC) No 2813/2000 of 21 December 2000 laying down detailed rules for the application of Council Regulation (EC) No 104/2000 as regards the grant of private storage aid for certain fishery products |  |  |  |  |
|  | 2814/2000/EC: Commission Regulation (EC) No 2814/2000 of 21 December 2000 laying down the detailed rules for the application of Council Regulation (EC) No 104/2000 as regards the grant of carry-over aid for certain fishery products |  |  |  |  |

Table 8.1.1 (Continued)

| No | Title and Number of EU legislation | Title of Draft Turkish legislation | Responsible Institution | Proposed Date of the Approval of the Minister / Council of Ministers | Proposed Date of 1- Adoption by the Parliament 2- Entry into Force |
| --- | --- | --- | --- | --- | --- |
|  | 80/2001/EC: Commission Regulation (EC) No 80/2001 of 16 January 2001 laying down detailed rules for the application of Council Regulation (EC) No 104/2000 as regards notifications concerning recognition of producer organisations, the fixing of prices and intervention within the scope of the common organisation of the market in fishery and aquaculture products |  |  |  |  |
|  | 939/2001/EC: Commission Regulation (EC) No 939/2001 of 14 May 2001 laying down detailed rules for the application of Council Regulation (EC) No 104/2000 as regards the grant of flat-rate aid for certain fishery products |  |  |  |  |
|  | 2318/2001/EC: Commission Regulation (EC) No 2318/2001 of 29 November 2001 laying down detailed rules for the application of Council Regulation (EC) No 104/2000 as regards the recognition of producer organisations in the fishery and aquaculture sector |  |  |  |  |
|  | 2065/2001/EC: Commission Regulation (EC) No 2065/2001 of 22 October 2001 laying down detailed rules for the application of Council Regulation (EC) No 104/2000 as regards informing consumers about fishery and aquaculture products |  |  |  |  |

Table 8.1.1 (Continued)

| No | Title and Number of EU legislation | Title of Draft Turkish legislation | Responsible Institution | Proposed Date of the Approval of the Minister / Council of Ministers | Proposed Date of 1- Adoption by the Parliament 2- Entry into Force |
| --- | --- | --- | --- | --- | --- |
|  | 150/2001/EC: Commission Regulation (EC) No 150/2001 of 25 January 2001 laying down detailed rules for the application of Council Regulation (EC) No 104/2000 as regards the penalties to be applied to producer organisations in the fisheries sector for irregularity of the intervention mechanism and amending Regulation (EC) No 142/98 |  |  |  |  |
|  | 1813/2001/EC: Commission Regulation (EC) No 1813/2001 of 14 September 2001 laying down the detailed rules for the application of Council Regulation (EC) No 104/2000 as regards the conditions for, the grant of and the withdrawal of recognition of interbranch organisations |  |  |  |  |
|  | 2574/2001/EC: Commission Regulation (EC) No 2574/2001 of 20 December 2001 fixing the reference prices for a number of fishery products for the fishing year 2002 |  |  |  |  |
| 6 | 2406/96/EC: Council Regulation (EC) No 2406/96 of 26 November 1996 laying down common marketing standards for certain fishery products | Implementing Regulation Amending the Implementing Regulation on Fisheries | Ministry of Agriculture and Rural Affairs (This legislation will be drafted with the participation of relevant institutions). | 30.06.2004 | 2- 15.07.2005 |

Table 8.1.1 (Continued)

| No | Title and Number of EU legislation | Title of Draft Turkish legislation | Responsible Institution | Proposed Date of the Approval of the Minister / Council of Ministers | Proposed Date of 1- Adoption by the Parliament 2- Entry into Force |
| --- | --- | --- | --- | --- | --- |
| Task 8.4 Fisheries Vessel Registration System |
| 1 | 2847/93/EEC: Council Regulation (EEC) No 2847/93 of 12 October 1993 establishing a control system applicable to the common fisheries policy 2930/86/EEC: Council Regulation (EEC) No 2930/86 of 22 September 1986 defining characteristics for fishing vessels 2090/98/EC: Commission Regulation (EC) No 2090/98 of 30 September 1998 concerning the fishing vessel register of the Community 84/95/EC: Commission Decision of 20 March 1995 concerning the implementation of the Annex to Council Regulation (EEC) No 2930/86 defining the characteristics of fishing vessels | Framework Law on Fisheries | Ministry of Agriculture and Rural Affairs (This legislation will be drafted with the participation of relevant institutions). | 30.06.2004 | 1- 15.06.2005 2- 15.07.2005 |
|  |  | Implementing Regulation Amending the Implementing Regulation on Fisheries | Ministry of Agriculture and Rural Affairs (This legislation will be drafted with the participation of relevant institutions). | 30.06.2004 | 2- 15.07.2005 |
| 2 | 1381/87/EEC: Commission Regulation (EEC) No 1381/87 of 20 May 1987 establishing detailed rules concerning the marking and documentation of fishing vessels | Framework Law on Fisheries | Ministry of Agriculture and Rural Affairs (This legislation will be drafted with the participation of relevant institutions). | 30.06.2004 | 1- 15.06.2005 2- 15.07.2005 |
| 3 | 839/2002/EC: Commission Regulation (EC) No 839/2002 of 21 May 2002 amending Regulation (EC) No 2090/98 concerning the fishing vessel register of the Community 3259/94/EC: Council Regulation (EC) No 3259/94 of 22 December 1994 amending Regulation (EEC) No 2930/86 defining the characteristics of fishing vessels | Circular on the classification of fishing vessels laying down the implementation principles of the Vessel Registration System | Ministry of Agriculture and Rural Affairs | 30.06.2004 | 2- 15.07.2005 |

Table 8.1.1 (Continued)

| No | Title and Number of EU legislation | Title of Draft Turkish legislation | Responsible Institution | Proposed Date of the Approval of the Minister / Council of Ministers | Proposed Date of 1- Adoption by the Parliament 2- Entry into Force |
| --- | --- | --- | --- | --- | --- |
| Task 8.5 Information Systems and Statistics |
| 1 | 2807/83/EEC: Commission Regulation (EEC) No 2807/83 of 22 September 1983 laying down detailed rules for recording information on Member States' catches of fish | Framework Law on Fisheries | Ministry of Agriculture and Rural Affairs (This legislation will be drafted with the participation of relevant institutions). | 30.06.2004 | 1- 15.06.2005 2- 15.07.2005 |
|  | 1382/91/EEC: Council Regulation (EEC) No 1382/91 of 21 May 1991 on the submission of data on the landings of fishery products in Member States | Implementing Regulation Amending the Implementing Regulation on Fisheries | Ministry of Agriculture and Rural Affairs (This legislation will be drafted with the participation of relevant institutions). | 30.06.2004 | 2- 15.07.2005 |
|  | 788/96/EC: Council Regulation (EC) No 788/96 of 22 April 1996 on the submission by Member States of statistics on aquaculture production |  |  |  |  |
|  | 1543/2000/EC: Council Regulation (EC) No 1543/2000 of 29 June 2000 establishing a Community framework for the collection and management of the data needed to conduct the common fisheries policy |  |  |  |  |
|  | 1639/2001/EC: Commission Regulation (EC) No 1639/2001 of 25 July 2001 establishing the minimum and extended Community programmes for the collection of data in the fisheries sector and laying down detailed rules for the application of Council Regulation (EC) No 1543/2000 |  |  |  |  |

Table 8.1.1 (Continued)

| No | Title and Number of EU legislation | Title of Draft Turkish legislation | Responsible Institution | Proposed Date of the Approval of the Minister / Council of Ministers | Proposed Date of 1- Adoption by the Parliament 2- Entry into Force |
| --- | --- | --- | --- | --- | --- |
|  | 2000/439/EC: 2000/439/EC: Council Decision of 29 June 2000 on a financial contribution from the Community towards the expenditure incurred by Member States in collecting data, and for financing studies and pilot projects for carrying out the common fisheries policy |  |  |  |  |
| 2 | 2945/95/EC: Commission Regulation (EC) No 2945/95 of 20 December 1995 amending Regulation (EEC) No 2807/83 laying down detailed rules for recording information on Member States' catches of fish | Circular on the implementation principles on the recording and notification of data related to fishery products | Ministry of Agriculture and Rural Affairs | 30.06.2004 | 2- 15.07.2005 |
|  | 2737/1999/EC: Commission Regulation (EC) No 2737/1999 of 21 December 1999 amending Regulation (EEC) No 2807/83 laying down detailed rules for recording information on Member States' catches of fish |  |  |  |  |
|  | 2104/1993/EC: Council Regulation (EEC) No 2104/93 of 22 July 1993 amending Regulation (EEC) No 1382/91 on the submission of data on the landings of fishery products in Member States |  |  |  |  |
|  | 2846/98/EC: Council Regulation (EC) No 2846/98 of 17 December 1998 amending Regulation (EEC) No 2847/93 establishing a control system applicable to the common fisheries policy |  |  |  |  |

Table 8.1.1 (Continued)

| No | Title and Number of EU legislation | Title of Draft Turkish legislation | Responsible Institution | Proposed Date of the Approval of the Minister / Council of Ministers | Proposed Date of 1- Adoption by the Parliament 2- Entry into Force |
| --- | --- | --- | --- | --- | --- |
|  | 2018/93/EEC: Council Regulation (EEC) No 2018/93 of 30 June 1993 on the submission of catch and activity statistics by Member States fishing in the Northwest Atlantic |  |  |  |  |
| 3 | 2847/93/EEC: Council Regulation (EEC) No 2847/93 of 12 October 1993 establishing a control system applicable to the common fisheries policy | Framework Law on Fisheries | Ministry of Agriculture and Rural Affairs (This legislation will be drafted with the participation of relevant institutions). | 30.06.2004 | 1- 15.06.2005 2- 15.07.2005 |
|  |  | Implementing Regulation Amending the Implementing Regulation on Fisheries | Ministry of Agriculture and Rural Affairs (This legislation will be drafted with the participation of relevant institutions). | 30.06.2004 | 2- 15.07.2005 |
|  |  | Implementing Regulation Amending the Implementing Regulation on Wholesale and Retail Sale Places of Fishery Products | Ministry of Agriculture and Rural Affairs (This legislation will be drafted with the participation of relevant institutions). | 30.06.2004 | 2- 15.07.2005 |
| Task 8.6 Food Hygiene in Fishery Products |
| 1 | 91/492/EEC: Council Directive 91/492/EEC of 15 July 1991 laying down the health conditions for the production and the placing on the market of live bivalve molluscs 91/493/EEC: Council Directive 91/493/EEC of 22 July 1991 laying down the health conditions for the production and the placing on the market of fishery products | Implementing Regulation Amending the Implementing Regulation on Fisheries | Ministry of Agriculture and Rural Affairs (This legislation will be drafted with the participation of relevant institutions). | 30.06.2004 | 2- 15.07.2005 |

Table 8.1.1 (Continued)

| No | Title and Number of EU legislation | Title of Draft Turkish legislation | Responsible Institution | Proposed Date of the Approval of the Minister / Council of Ministers | Proposed Date of 1- Adoption by the Parliament 2- Entry into Force |
| --- | --- | --- | --- | --- | --- |
| 2 | 79/923/EEC: Council Directive 79/923/EEC of 30 October 1979 on the quality required of shellfish waters | Circular amending the Circular on the quality criteria regarding the production areas of bivalve molluscs | Ministry of Agriculture and Rural Affairs | 30.06.2004 | 2- 15.07.2005 |
| 3 | 80/778/EEC: Council Directive 80/778/EEC of 15 July 1980 relating to the quality of water intended for human consumption | Circular on the implementation of the Implementing Regulation of the Ministry of Health published in the Official Gazette no 23144 of 18 October 1997 on the Production, Packaging, Sale and Control of Water Intended for Human Consumption | Ministry of Agriculture and Rural Affairs Ministry of Health | 30.06.2004 | 2- 15.07.2005 |
| 4 | 90/675/EEC: Council Directive 90/675/EEC of 10 December 1990 laying down the principles governing the organization of veterinary checks on products entering the Community from third countries | Law amending Law no 3285 on Animal Health and Surveillance | Ministry of Agriculture and Rural Affairs | 30.06.2004 | 1- 15.06.2005 2- 15.07.2005 |
| 5 | 91/67/EEC: Council Directive 91/67/EEC of 28 January 1991 concerning the animal health conditions governing the placing on the market of aquaculture animals and products | Framework Law on Fisheries | Ministry of Agriculture and Rural Affairs (This legislation will be drafted with the participation of relevant institutions). | 30.06.2004 | 1- 15.06.2005 2- 15.07.2005 |
|  | 93/53/EEC: Council Directive 93/53/EEC of 24 June 1993 introducing minimum Community measures for the control of certain fish diseases | Implementing Regulation Amending the Implementing Regulation on Fisheries | Ministry of Agriculture and Rural Affairs (This legislation will be drafted with the participation of relevant institutions). | 30.06.2004 | 2- 15.07.2005 |

Table 8.1.1 (Continued)

| No | Title and Number of EU legislation | Title of Draft Turkish legislation | Responsible Institution | Proposed Date of the Approval of the Minister / Council of Ministers | Proposed Date of 1- Adoption by the Parliament 2- Entry into Force |
| --- | --- | --- | --- | --- | --- |
|  | 94/356/EC: Commission Decision of 20 May 1994 laying down detailed rules for the application of Council Directive 91/493/EEC, as regards own health checks on fishery products |  |  |  |  |
|  | 95/149/EC: Commission Decision of 8 March 1995 fixing the total volatile basic nitrogen (TVB-N) limit values for certain categories of fishery products and specifying the analysis methods to be used |  |  |  |  |
|  | 1093/94/EC: Council Regulation (EC) No 1093/94 of 6 May 1994 setting the terms under which fishing vessels of a third country may land directly and market their catches at Community ports |  |  |  |  |
| 6 | 92/48/EEC: Council Directive 92/48/EEC of 16 June 1992 laying down the minimum hygiene rules applicable to fishery products caught on board certain vessels in accordance with Article 3 (1) (a) (i) of Directive 91/493/EEC | Circular laying down the implementation principles of hygiene rules for processed fishery products | Ministry of Agriculture and Rural Affairs | 30.06.2004 | 2- 15.07.2005 |
| 7 | 93/140/EEC: Commission Decision of 19 January 1993 laying down the detailed rules relating to the visual inspection for the purpose of detecting parasites in fishery products | Circular laying down the implementation principles of parasite controls for fishery products | Ministry of Agriculture and Rural Affairs | 30.06.2004 | 2- 15.07.2005 |

Table 8.1.1 (Continued)

| No | Title and Number of EU legislation | Title of Draft Turkish legislation | Responsible Institution | Proposed Date of the Approval of the Minister / Council of Ministers | Proposed Date of 1- Adoption by the Parliament 2- Entry into Force |
| --- | --- | --- | --- | --- | --- |
| Task 8.7 Aquaculture |
| 1 | 104/2000/EC: Council Regulation (EC) No 104/2000 of 17 December 1999 on the common organisation of the markets in fishery and aquaculture products | Framework Law on Fisheries | Ministry of Agriculture and Rural Affairs (This legislation will be drafted with the participation of relevant institutions). | 30.06.2004 | 1- 15.06.2005 2- 15.07.2005 |
|  |  | Law on Agricultural Producer Unions, relevant Decisions of Council of Ministers and Implementing Regulations | Ministry of Agriculture and Rural Affairs | 2003, Third Quarter | 1- 2003, Fourth Quarter 2- January 2004 |
|  |  | Implementing Regulation Amending the Implementing Regulation on Fisheries | Ministry of Agriculture and Rural Affairs (This legislation will be drafted with the participation of relevant institutions). | 30.06.2004 | 2- 15.07.2005 |
|  |  | Implementing Regulation Amending the Implementing Regulation on Wholesale and Retail Sale Places of Fishery Products | Ministry of Agriculture and Rural Affairs (This legislation will be drafted with the participation of relevant institutions). | 30.06.2004 | 2- 15.07.2005 |
|  |  | Circular on Fisheries | Ministry of Agriculture and Rural Affairs (This legislation will be drafted with the participation of relevant institutions). | 30.06.2004 | 2- 15.07.2005 |
| 2 | 91/67/EEC: Council Directive 91/67/EEC of 28 January 1991 concerning the animal health conditions governing the placing on the market of aquaculture animals and products 93/53/EEC: Council Directive 93/53/EEC of 24 June 1993 introducing minimum Community measures for the control of certain fish diseases | Framework Law on Fisheries | Ministry of Agriculture and Rural Affairs (This legislation will be drafted with the participation of relevant institutions). | 30.06.2004 | 1- 15.06.2005 2- 15.07.2005 |
|  |  | Implementing Regulation Amending the Implementing Regulation on Fisheries | Ministry of Agriculture and Rural Affairs (This legislation will be drafted with the participation of relevant institutions). | 30.06.2004 | 2- 15.07.2005 |

##### 3- Schedule of Necessary Institutional Changes

Table 8.1.2

| No | Necessary Institutional Changes – (Ministry of Agriculture and Rural Affairs) | Period of Implementation |
| --- | --- | --- |
| 1 | Restructuring of the Ministry of Agriculture and Rural Affairs for the management and guidance of the sector and for the harmonisation and efficient implementation of the EU fisheries legislation (Establishment of Directorate General for Fisheries or a similar autonomous body) | June 2004-May 2005 |
| 2 | Receiving technical assistance for the preparation of fisheries legislation in harmony with the EU legislation | 2004-2005 |
| 3 | Receiving technical assistance for the preparation and implementation of sector development plan | November 2004-November 2005 |
| 4 | Receiving technical assistance for the preparation of fisheries policy and for the establishment of a Fisheries Policy and Planning Unit within MARA, meeting infrastructural requirements and training of relevant staff | November 2004-December 2005 |
| 5 | Training of the fisheries management and sector stakeholders | May 2005-October 2006 |
| 6 | Receiving technical assistance for strengthening the participation of relevant stakeholders to the fisheries management | 2004-2005 |
| 7 | Receiving technical assistance for the implementation of all main conservation and control components of the EU fisheries legislation and training of adequate number of staff | March 2005-April 2006 |
| 8 | Receiving technical assistance for the establishment of fisheries port offices at 30 fishery ports, meeting land and infrastructural investment needs, employment of new staff, allocation of personnel, full-functioning of 30 fishery ports and integration of these ports with a prospective central information system | March 2005-February 2006 |
| 9 | Receiving technical assistance for the preparation of resource management policy and draft fisheries management plans for all significant fisheries activities through scientific advice and consensus among relevant parties | December 2004-October 2005 |
| 10 | Receiving technical assistance for the establishment of a Fisheries Information System (FIS) functioning at national and regional levels that meets EU legal requirements | January 2005-October 2006 |
| 11 | Receiving technical assistance for the establishment of a national fisheries vessel registration system in compliance with EU requirements, establishment of the system and training of staff | March 2005-February 2006 |
| 12 | Receiving technical assistance for the establishment of a Fisheries Monitoring Center (FMC) and Vessel Monitoring System (VMS) at MARA and for the functioning of this system, and meeting infrastructural investment requirements | February 2005-June 2006 |
| 13 | Training of the managers and technical personnel who will be in charge of carrying out the Fisheries Information System for the rational management of fisheries resources | January 2005-April 2006 |

Table 8.1.2 (Continued)

| No | Necessary Institutional Changes – (Ministry of Agriculture and Rural Affairs) | Period of Implementation |
| --- | --- | --- |
| 14 | Adoption and implementation of a transparent system enabling producers to reach a balance between demand and supply and ensuring the operation of the fisheries market, and receiving technical assistance on the local control of fish markets and on the design of a model market | September-October 2005 |
| 15 | Training of control experts and producers on the freshness and size grading standards of EU fishery products | February-March 2005 |
| 16 | Receiving technical assistance for the implementation of an intervention system with a designated minimum price for unsalable products | May-June 2006 |
| 17 | Receiving technical assistance for the establishment of a market information statistical reporting and analysis system including trade information and data gathered from ports and other first hand markets; and the establishment of the system | July 2005 |

##### 4- Financing Requirements and Sources of Financing1)

Table 8.1.3 																		(Euro)

| Requirements - (Ministry of Agriculture and Rural Affairs) | Year | National Budget | EU Resources | Other Resources | Total |
| --- | --- | --- | --- | --- | --- |
| I-Investment Computer hardware for Fisheries Policy and Planning Unit Establishment of 30 port offices and supplying the ports with necessary equipment Infrastructural investments for the establishment of Fisheries Monitoring Center and Vessel Monitoring System (including computers, printers and software) | 2004 | 223,750 | 671,250 |  | 895,000 |
|  | 2005 | 210,389 | 631,167 |  | 841,556 |
| II- Harmonisation with the EU Legislation and Implementation |
| Recruitment of Personnel a) | 2004 |  |  |  |  |
|  | 2005 |  |  |  |  |

Table 8.1.3 (Continued)																	(Euro)

| Requirements - (Ministry of Agriculture and Rural Affairs) | Year | National Budget | EU Resources | Other Resources | Total |
| --- | --- | --- | --- | --- | --- |
| Traininga) Workshops for the preparation of the fisheries legislation Study visit on institutional strengthening (5 persons x10 days) Workshops for institutional strengthening Study visits on the establishment of the Fisheries Policy and Planning Unit (5 persons x10 days) Workshops on the establishment of the Fisheries Policy and Planning Unit Workshops and public seminars for strengthening the participation of stakeholders in the fisheries management | 2004 |  | (Twinning) 405,300 (Technical Assistance) 166,253 |  | 571,553 |
|  | 2005 |  | (Twinning) 360.950 (Technical Assistance) 337,251 |  | 698,201 |
| Training of staff on conservation and control policies Seminars and courses for senior staff (20 persons x 5 days) Courses for port fishery officers (20 persons x 12 days) Courses for Coast Guard staff (20 persons x 12 days) Seminars for port staff (20 persons x 12 days) Study visits (15 persons x 10 days) Workshops providing scientific advice on the preparation of fishery management plans Study visits providing scientific advice on the preparation of fishery management plans (15 persons x 10 days) Participation in international meetings providing scientific advice on the preparation of fishery management plans (5 persons x 5 days) Study visits on the development and implementation of the legislation on fisheries common market organisation (20 persons x 14 days) Market training (10 x 20 persons x3 days) Workshops on the establishment of fisheries vessel registration system Study visits on the establishment of fisheries vessel registration system (5 persons x10 days) Workshops on the establishment of fisheries monitoring system |  |  |  |  |  |

Table 8.1.3 (Continued)																	(Euro)

| Requirements - (Ministry of Agriculture and Rural Affairs) | Year | National Budget | EU Resources | Other Resources | Total |
| --- | --- | --- | --- | --- | --- |
| Consultancy 4 Turkish and 3 foreign experts on the preparation of sector strategy and sector plan Turkish experts and 2 foreign experts on the preparation of fisheries legislation Pre-accession advisor and his/her assistant on institutional strengthening 1 Turkish and 1 foreign expert on the establishment of Fisheries Policy and Planning Unit 1 Turkish and 1 foreign expert on strengthening stakeholder participation in fisheries management Pre-accession advisor and his/her assistant on conservation and control policies 1 Turkish expert on the establishment of 30 port offices and provision of necessary equipment | 2004 |  | (Twinning) 895,730 (Technical Assistance) 1,242,397 |  | 2,138,127 |
|  | 2005 |  | (Twinning) 761,180 (Technical Assistance) 617,906 |  | 1,379,086 |
| 1 Turkish and 3 foreign experts providing scientific advice on the preparation of fisheries management plans Pre-accession advisor and his/her assistant on the development and implementation of the legislation on fisheries common market organisation 1 foreign and 2 Turkish experts on the local control of fish markets 1 Turkish expert and 1 foreign expert on market financing 1 Turkish expert and 1 foreign expert on market statistics 2 Turkish experts on model market designing 1 Turkish and 1 foreign information processing experts on the institutional strengthening of Fisheries Information System 1 foreign expert on the establishment of Fisheries Monitoring Center and Vessel Monitoring System 1 Turkish expert and 1 foreign expert on the establishment of Fisheries Vessel Registration System 1 foreign expert on the establishment and design of Fisheries Monitoring System and on the development of relevant training programmes |  |  |  |  |  |

Table 8.1.3 (Continued)																	(Euro)

| Requirements - (Ministry of Agriculture and Rural Affairs) | Year | National Budget | EU Resources | Other Resources | Total |
| --- | --- | --- | --- | --- | --- |
| Translation | 2004 |  | (Twinning) 14,250 (Technical Assistance) 29,250 |  | 43,500 |
|  | 2005 |  | (Twinning) 9,750 (Technical Assistance) 9,000 |  | 18,750 |
| Other |  |  |  |  |  |
| Land allocation for the establishment of 30 port offices | 2004 | 238,000 |  |  | 238,000 |
| Office accommodation for the experts working on the project |  |  |  |  |  |
| Operational expenses of research institutes reporting to MARA | 2005 | 231,000 |  |  | 231,000 |
| Total |  | 903,139 | 6,151,634 |  | 7,054,773 |

a) Financing requirements will be redefined in detail, according to the technical assistance received.

# Footnotes

1) The financing requirements table of the  “Establishment of Legal Framework for the Alignment to the Common Fisheries Policy” priority overlaps with the budgetary requirements of the “Fisheries Sector-Legal and Institutional Alignment to the EU Acquis Project”, proposed under the 2003 Pre-accession Financial Assistance Programme. Therefore, for financial details of this priority the budget of the project should be referred to.