## Slide 1: Lessons learned from IPA 2021-2022 programming

## Slide 2: Context
IPA III novelties (Windows, lack of country allocations, project-based approach, etc.)
EU legislation in place
Original recommendation by the Commission to submit as many projects as possible
Submission of 330+ Action Fiches to the tune of approx. €3.5 billion – each IPA body prepared dozens of Action Fiches
Rejection on the level of Action Fiche and then Action Document (accompanied by draft technical/tender documents): 2 phased approach
Pre-selection criteria:
  Relevance
  Maturity
  Sometimes reference to sustainability
Budget cuts for the entire IPA envelope in the initial period (all IPA III countries) means it is not business as usual
Need for some smart approaches
Acquis alignment is priority

## Slide 3: Lessons learned and what can be done
Prioritisation on the level of Managing Authority and Intermediate Body (relevance ranking)
Prioritisation on the level of Presidency of Strategy and Budget (relevance ranking)
Prioritisation on the level of NIPAC (collective relevance ranking)
Best if projects are about alignment with the relevant Acquis chapter
Linking relevance with maturity at the AF level
Non-value added projects and those only relevant on strategic level must be avoided
Instruction in AF is insufficient to win; more technical content is required (to be discussed during after afternoon session), also: some activity description shall be included before the logframe
Relevance shall be linked to the actual needs of the target group (clear gap assessment), which exemplifies internal consistency of the project (and is clearly linked to the logframe)
Relevance shall also be linked to maturity (as it takes time to prepare technical/tender documents); sometimes ideas are well-grounded but they will remain only as ideas for years to come or risk insufficient results (also similar previous projects)

## Slide 4: Lessons learned and what can be done
Virtually, no room for investment projects financed as previously
Need for living/evolving project pipeline
Relevance is not about being black or white – there are different shades of grey
Causal association with: Accession partnership, Country progress report, National plan for adoption of acquis, Acquis chapter alignment, NDP, ERP, Reference to SDG (minor as it is only about OECD-DAC codes), alignment with the relevant EU strategies and priorities
Avoid fragmented projects and provide clear evidence for coordination/ownership
Vision to link interventions with Turkish Investment Platform (TIP) which mirrors Western Balkan Investment Framework (WBIF)
Demarcation line between IPA funds and TIP is required
A 2-3 phased approach is recommended

## Slide 5
This document has been produced with the financial assistance of the European Union. The contents of this publication are the sole responsibility of WEglobal and can in no way be taken to reflect the views of the European Union or Directorate of EU Affairs of the Ministry for Foreign Affairs of the Republic of Turkey (Türkiye).

## Slide 6: THANK YOU